Dashboard 1 — Executive Portfolio Decision View

PPM Decision Intelligence | Dashboard Specification & QA Record

Purpose. Provide executives with a portfolio-level view of financial exposure, delivery performance, resource-capacity pressure, and projects requiring prioritized intervention.

Figure 1. Certified December 2026 executive dashboard.

# 1. Dashboard Components

| Component | Business purpose |
| --- | --- |
| Portfolio Budget | Quantify total approved investment exposure. |
| Forecast Cost | Show expected portfolio financial outcome. |
| CPI | Assess portfolio cost efficiency. |
| SPI | Assess portfolio schedule efficiency. |
| Projects at Risk | Quantify the At Risk/Critical project population. |
| Portfolio Budget Concentration | Identify the largest financial exposures. |
| Delivery Risk Concentration | Identify projects with the greatest forecast schedule delay. |
| Role Capacity Pressure | Identify constrained delivery capabilities. |
| High-Value Projects at Risk | Prioritize strategically important projects with schedule underperformance and material financial exposure. |

# 2. Analytical Data Sources & Grain

Project Performance — one row per Project × Reporting Month. Drives KPI 01–05 and VIZ 01, VIZ 02, and VIZ 04.

Resource Capacity — one row per Resource Role × Reporting Month. Drives VIZ 03.

Modeling decision. The sources are not physically joined. Their grains are different, and a direct join without a valid project-role allocation key could create many-to-many duplication. A common reporting-period field synchronizes the dashboard while preserving each dataset's analytical grain.

# 3. Tableau Business Logic

Projects at Risk — Counts distinct projects whose overall health is At Risk or Critical.

COUNTD(
    IF [Health Status] = "At Risk"
    OR [Health Status] = "Critical"
    THEN [Project Id]
    END
)

Executive Zone Label — Labels projects in the defined executive-attention zone.

IF [Strategic Importance Score] >= 80
AND [Spi] < 0.90
THEN [Project Name]
END

Forecast Overrun — Optional supporting calculation for forecast-versus-approved-budget analysis.

SUM([Forecast Cost]) - SUM([Approved Budget])

# 4. Reporting-Period Filter Architecture

Visible control: Reporting Period (Single Value Dropdown).

Primary field: Period Start Date.

Scope: all worksheets using related data sources.

One visible control synchronizes Project Performance and Resource Capacity without physically joining the two datasets.

QA defect caught during testing: VIZ 03 initially retained an obsolete December-only local filter. When cross-data-source filtering was enabled, the two filters conflicted and blanked the resource-capacity view for other months. Removing the redundant local filter restored synchronized behavior.

# 5. December 2026 Regression Controls

| Control | Certified value |
| --- | --- |
| Portfolio Budget | $817.1M |
| Forecast Cost | $858.2M |
| Average CPI | 0.97 |
| Average SPI | 0.95 |
| Projects At Risk | 16 (10.7% of portfolio) |
| Largest Budget Exposure | Fusion Process Automation — ~$39.7M |
| Largest Schedule Delay | Wave Process Automation — 129 days |
| Highest Role Utilization | Data Engineer — 118.7% |
| Executive Attention Zone | Rise Digital Commerce |

# 6. QA Certification

| Test | Validation | Result |
| --- | --- | --- |
| QA-01 | Reporting-period synchronization | PASS |
| QA-02 | KPI reconciliation | PASS |
| QA-03 | Budget ranking | PASS |
| QA-04 | Delivery-risk ranking | PASS |
| QA-05 | Capacity integrity | PASS |
| QA-06 | Executive-priority logic | PASS |
| QA-07 | Interaction / edge-case stress test | PASS |

Certification result: 7/7 tests passed.

# 7. Executive Findings

Financial: forecast cost exceeds approved portfolio budget.

Delivery: schedule performance is weaker than cost performance in the December 2026 snapshot.

Risk: 16 of 150 projects are At Risk/Critical.

Capacity: multiple specialized delivery roles operate above available capacity.

Prioritization: Rise Digital Commerce occupies the defined high-strategic-value / low-SPI intervention zone and carries meaningful financial exposure.

Interpretive boundary: portfolio-level capacity pressure coincides with concentrated delivery risk, but the current data grain does not establish project-level resource causality.

# 8. Design Decisions

Fixed 1200 × 800 dashboard designed for practical laptop viewing.

Five-card KPI strip plus four analytical views; no additional insight panel was added because available real estate was intentionally protected for readability.

Color is semantic rather than decorative: neutral information, attention, and intervention states are visually distinguished.

Dashboard 1 is frozen after QA certification; future changes should be regression-tested against the December 2026 controls above.