PPM DECISION INTELLIGENCE

# Executive Decision Canvas

Specification & Traceability Record

Certified reference state: December 2026

# 1. Purpose

The Executive Decision Canvas is the decision-intelligence layer above the four certified Tableau dashboards. Its purpose is to compress portfolio evidence into a traceable management sequence: Situation → Evidence → Priority → Action → Monitoring. It is not a fifth dashboard and does not introduce a new analytical dataset.

# 2. Certified Canvas Statement

Situation: The portfolio is experiencing simultaneous financial, schedule, risk, and resource pressure. These pressures are unevenly distributed, requiring targeted intervention rather than portfolio-wide corrective action.

| Headline signal | December 2026 baseline | Primary evidence source |
| --- | --- | --- |
| Forecast Overrun | $33.1M | Dashboard 4 — Project Performance & Forecast Control |
| Projects Delayed | 94 / 150 | Dashboard 4 — Project Performance & Forecast Control |
| Unresolved Risks | 32 | Dashboard 2 — Portfolio Risk & Intervention |
| Capacity Coverage | 95.0% | Dashboard 3 — Resource Capacity & Delivery Readiness |

# 3. Evidence Traceability

| Canvas evidence | Certified fact | Source / interpretation |
| --- | --- | --- |
| Financial | 100 of 150 projects forecast over current budget. | Dashboard 4. Broad financial pressure; magnitude differs by project. |
| Delivery | 71 projects are both forecast over budget and delayed. | Dashboard 4 VIZ 15 diagnostic. Establishes co-occurrence, not causality. |
| Risk | 16 of 32 unresolved risks are High/Critical. | Dashboard 2. Severe Risk Share = 50.0%; 27 projects exposed. |
| Capacity | Planned demand exceeds available capacity by 1,700 hours; 10 of 12 roles are under pressure. | Dashboard 3. Planned demand 34,180 hours; available capacity 32,480 hours. |
| Synthesis | Pressure is material, but concentrated intervention is more appropriate than uniform action. | Professional judgment derived from the uneven distribution of financial, delivery, risk and capacity signals. |

# 4. Priority Framework

| Priority | Definition | Use |
| --- | --- | --- |
| P1 — Immediate Executive Review | Multiple adverse signals converge. | Escalate the highest-priority projects for executive review of recovery options, commitments and intervention. |
| P2 — Targeted Management Intervention | Material adverse signal in one principal dimension. | Address the specific financial, schedule or risk issue without assuming portfolio-wide deterioration. |
| P3 — Monitor | No current evidence requires active intervention. | Continue routine monitoring and watch for movement into material pressure. |
| Portfolio Capacity Intervention | Planned demand exceeds specialist capacity. | Treat capacity as a portfolio delivery-system constraint, not solely as an individual project issue. |

Governance note: P1/P2/P3 is a recommended intervention framework. The current dataset does not contain a historical monthly P1/P2/P3 classification, so the project does not claim historical movement between these tiers.

# 5. Recommended Executive Actions

1. Launch focused project recovery reviews

Begin with the 71 projects under combined financial and schedule pressure, then prioritize using overrun magnitude, delay, unresolved risk, health status and strategic importance.

2. Challenge forecasts and remaining commitments

For materially over-budget projects, review forecast assumptions and determine whether to accept the revised forecast, pursue corrective action, modify scope/timing, or reconsider remaining commitment.

3. Rebalance constrained specialist capacity

Review demand and supply options. Initial attention includes Functional Consultant (largest absolute shortfall: 570 hours) and Data Engineer (highest relative demand pressure: approximately 118.8%).

4. Escalate severe unresolved risks

Prioritize severe unresolved risks according to exposure and convergence with other adverse signals rather than raw risk count alone.

5. Establish a monthly intervention cycle

Repeat the portfolio assessment each reporting period to determine what changed, whether interventions are working, and where leadership attention should shift.

# 6. Monitoring Framework

| Signal | December baseline | Desired direction / trigger |
| --- | --- | --- |
| Forecast Overrun | $33.1M | Down; investigate material deterioration or lack of improvement after intervention. |
| Combined Pressure | 71 / 150 | Down; track projects leaving or entering the over-budget + delayed condition. |
| Severe Unresolved Risk | 16 High/Critical | Down, especially among priority projects; validate real mitigation rather than administrative closure. |
| Capacity Coverage | 95.0% | Toward/above 100%, while also checking role-level constraints. |
| Intervention Movement | P1 <-> P2 <-> P3 | Once adopted, record monthly tier status and assess improvement, persistence or deterioration. |

# 7. Evidence → Judgment → Decision Boundary

| Layer | What is supported |
| --- | --- |
| Observed evidence | Certified KPI values, project counts, risk counts, capacity measures, ranked projects and role pressures from Dashboards 1–4. |
| Analytical synthesis | The portfolio has simultaneous pressures and those pressures are unevenly distributed. |
| Professional judgment | Converging adverse signals warrant greater management attention than isolated or lower-pressure signals. |
| Recommended decision/action | Use P1/P2/P3 prioritization, focused recovery reviews, forecast challenge, capacity rebalancing, risk escalation and monthly intervention review. |

The recommendations are decision support, not automated decisions. Professional judgment remains between evidence and action.

# 8. Assumptions and Limitations

The project uses realistic synthetic Oracle PPM-style data; findings demonstrate analytical and decision-support methods rather than conditions in a real organization.

Current Budget is Dashboard 4's operational control baseline; Approved Budget remains the strategic/original baseline used elsewhere.

Forecast Overrun is Forecast Cost minus Current Budget; positive values are adverse.

Open Risk Burden is a prioritization index based on unresolved risk scores, not monetary exposure.

Financial overrun, schedule delay, risk and capacity pressure may co-occur; the analysis does not claim that one causes another.

No arbitrary organizational escalation thresholds are invented where the dataset provides none.

Capacity Coverage is a portfolio aggregate; role-level pressure must also be reviewed because aggregate improvement can mask specialist constraints.

Historical P1/P2/P3 intervention movement is recommended for future governance but is not present in the current source data.

# 9. QA and Governance Controls

| Control | Status |
| --- | --- |
| Canvas headline values reconcile to certified dashboard controls | PASS |
| Action sequence matches approved intervention logic | PASS |
| Observed facts are distinguished from professional judgment | PASS |
| No causal claims inferred from co-occurrence | PASS |
| No invented ROI, savings or escalation thresholds | PASS |
| P1/P2/P3 presented as recommended framework, not historical source data | PASS |
| Monitoring baselines reconcile to December 2026 certified state | PASS |

# 10. Artifact and Repository Record

Canonical artifact: Executive Decision Canvas (one-page PDF)
Recommended repository path: assets/decision-canvas/executive_decision_canvas.pdf
Specification: docs/decision-intelligence/executive_decision_canvas_spec_traceability.docx

Freeze rule: any change to the canvas must preserve traceability to certified dashboard evidence, distinguish evidence from judgment, and trigger revalidation of affected December 2026 controls.

# 11. Decision Intelligence Chain

DATA → EVIDENCE → INSIGHT → PROFESSIONAL JUDGMENT → DECISION → ACTION